## Phase
Project | Duy Tan Online Judge | [10 empty] | Create Date | [5 empty] | Creator
ID | [11 empty] | Updated Date | [5 empty] | Update
[12 empty] | Approved Date | [5 empty] | Approver
No | ID | Phase | Task | Task Detail | Resource |  |  |  | Plan |  |  |  |  | Performance |  |  |  |  | Actual
[5 empty] | AnhMV | AnhPV | TongTB | Status | Start | Finish | Duration (Days) | Hour | Cost | Start | Finish | Duration (Days) | Hour | Cost | Start | Finish | Duration (Days) | Hour | Cost
1 | LA.PP | Lauching | Create Proposal | Create Introduction | x |  |  | Closed | 2012-09-04 | 2012-09-04 | 0 | 2 | 4 | 2012-09-04 | 2012-09-04 | 0 | 2 | 4 | 2012-09-04 | 2012-09-04 | 0 | 2 | 4
2 | LA.PP | Lauching | Create Proposal | Create Vision |  | x |  | Closed | 2012-09-04 | 2012-09-04 | 0 | 2 | 3 | 2012-09-04 | 2012-09-04 | 0 | 2 | 3 | 2012-09-04 | 2012-09-04 | 0 | 2 | 3
3 | LA.PP | Lauching | Create Proposal | Create Object |  |  | x | Closed | 2012-09-04 | 2012-09-04 | 0 | 2 | 3 | 2012-09-04 | 2012-09-04 | 0 | 2 | 3 | 2012-09-04 | 2012-09-04 | 0 | 2 | 3
4 | LA.PP | Lauching | Create Proposal | Create Goals | x |  |  | Closed | 2012-09-05 | 2012-09-05 | 0 | 2 | 4 | 2012-09-05 | 2012-09-05 | 0 | 2 | 4 | 2012-09-05 | 2012-09-05 | 0 | 2 | 4
5 | LA.PP | Lauching | Create Proposal | Create Approach |  | x |  | Closed | 2012-09-05 | 2012-09-05 | 0 | 2 | 3 | 2012-09-05 | 2012-09-05 | 0 | 2 | 3 | 2012-09-05 | 2012-09-05 | 0 | 2 | 3
6 | LA.PP | Lauching | Create Proposal | Create Milestone |  |  | x | Closed | 2012-09-05 | 2012-09-05 | 0 | 2 | 3 | 2012-09-05 | 2012-09-05 | 0 | 2 | 3 | 2012-09-05 | 2012-09-05 | 0 | 2 | 3
7 | LA.PP | Lauching | Create Proposal | Create Resource |  | x |  | Closed | 2012-09-06 | 2012-09-06 | 0 | 2 | 3 | 2012-09-06 | 2012-09-06 | 0 | 2 | 3 | 2012-09-06 | 2012-09-06 | 0 | 2 | 3
8 | LA.PP | Lauching | Create Proposal | Create Approval | x |  |  | Closed | 2012-09-06 | 2012-09-06 | 0 | 2 | 4 | 2012-09-06 | 2012-09-06 | 0 | 2 | 4 | 2012-09-06 | 2012-09-06 | 0 | 2 | 4
9 | LA.TN | Lauching | Trainning | Learn and understand requirement | x | x | x | Closed | 2012-09-07 | 2012-09-07 | 0 | 3 | 15 | 2012-09-07 | 2012-09-07 | 0 | 3 | 15 | 2012-09-07 | 2012-09-07 | 0 | 3 | 15
10 | LA.TN | Lauching | Trainning | Analysis SRS sample | x | x | x | Closed | 2012-09-08 | 2012-09-08 | 0 | 3 | 15 | 2012-09-08 | 2012-09-08 | 0 | 3 | 15 | 2012-09-08 | 2012-09-08 | 0 | 3 | 15
11 | LA.TN | Lauching | Trainning | DB Design document | x | x | x | Closed | 2012-09-09 | 2012-09-09 | 0 | 3 | 15 | 2012-09-09 | 2012-09-09 | 0 | 3 | 15 | 2012-09-09 | 2012-09-09 | 0 | 3 | 15
12 | LA.TN | Lauching | Trainning | Interface design document | x | x | x | Closed | 2012-09-10 | 2012-09-11 | 1 | 6 | 30 | 2012-09-10 | 2012-09-11 | 1 | 6 | 30 | 2012-09-10 | 2012-09-11 | 1 | 6 | 30
13 | LA.TN | Lauching | Trainning | MVC | x | x | x | Closed | 2012-09-12 | 2012-09-12 | 0 | 4 | 20 | 2012-09-12 | 2012-09-12 | 0 | 4 | 20 | 2012-09-12 | 2012-09-12 | 0 | 4 | 20
14 | RE.ANA | Requirement | Analysis Requirement | Collection requirements | x | x | x | Closed | 2012-09-13 | 2012-09-13 | 0 | 4 | 20 | 2012-09-13 | 2012-09-13 | 0 | 4 | 20 | 2012-09-13 | 2012-09-13 | 0 | 4 | 20
15 | RE.ANA | Requirement | Analysis Requirement | Analysis requirements | x | x | x | Closed | 2012-09-17 | 2012-09-18 | 1 | 8 | 40 | 2012-09-17 | 2012-09-18 | 1 | 8 | 40 | 2012-09-17 | 2012-09-18 | 1 | 8 | 40
16 | RE.ANA | Requirement | Analysis Requirement | Remove requirement | x | x | x | Closed | 2012-09-14 | 2012-09-14 | 0 | 4 | 20 | 2012-09-14 | 2012-09-14 | 0 | 4 | 20 | 2012-09-14 | 2012-09-14 | 0 | 4 | 20
17 | RE.SRS | Requirement | Create SRS | Create Introduction | x |  |  | Closed | 2012-09-19 | 2012-09-20 | 1 | 8 | 16 | 2012-09-19 | 2012-09-20 | 1 | 8 | 16 | 2012-09-19 | 2012-09-20 | 1 | 8 | 16
18 | RE.SRS | Requirement | Create SRS | Create Overall Description |  | x |  | Closed | 2012-09-21 | 2012-09-23 | 2 | 12 | 18 | 2012-09-21 | 2012-09-23 | 2 | 12 | 18 | 2012-09-21 | 2012-09-23 | 2 | 12 | 18
19 | RE.SRS | Requirement | Create SRS | Create Users classes and Characterisstics |  | x |  | Closed | 2012-09-24 | 2012-09-25 | 1 | 8 | 12 | 2012-09-24 | 2012-09-25 | 1 | 8 | 12 | 2012-09-24 | 2012-09-25 | 1 | 8 | 12
20 | RE.SRS | Requirement | Create SRS | Create System Features | x | x | x | Closed | 2012-09-26 | 2012-09-28 | 2 | 12 | 60 | 2012-09-26 | 2012-09-28 | 2 | 12 | 60 | 2012-09-26 | 2012-09-30 | 4 | 12 | 60
21 | RE.SRS | Requirement | Create SRS | Create External Interface Requirements | x | x | x | Pending | 2012-09-29 | 2012-10-01 | 2 | 12 | 60 | 2012-09-29 | 2012-10-01 | 2 | 12 | 60 | 2012-09-29 | 2012-10-01 | 2 | 6 | 30
22 | RE.SRS | Requirement | Create SRS | Create Other Nonfunctional Requirements |  | x | x | Closed | 2012-09-29 | 2012-10-01 | 2 | 12 | 36 | 2012-09-29 | 2012-09-30 | 1 | 12 | 36 | 2012-09-29 | 2012-10-01 | 2 | 5 | 15
23 | DE.DB | Design | Database Design | Create Introduction |  | x |  | Closed | 2012-10-02 | 2012-10-02 | 0 | 4 | 6 | 2012-10-02 | 2012-10-02 | 0 | 4 | 6 | 2012-10-02 | 2012-10-02 | 0 | 4 | 6
24 | DE.DB | Design | Database Design | Create scope |  | x |  | Closed | 2012-10-03 | 2012-10-03 | 0 | 4 | 6 | 2012-10-03 | 2012-10-03 | 0 | 4 | 6 | 2012-10-03 | 2012-10-03 | 0 | 4 | 6
25 | DE.DB | Design | Database Design | Create sub application/Application Overview |  | x |  | Closed | 2012-10-04 | 2012-10-05 | 1 | 8 | 12 | 2012-10-04 | 2012-10-05 | 1 | 8 | 12 | 2012-10-04 | 2012-10-05 | 1 | 8 | 12
26 | DE.DB | Design | Database Design | Create table relationship diagrams |  | x |  | Closed | 2012-10-04 | 2012-10-10 | 6 | 24 | 36 | 2012-10-04 | 2012-10-10 | 6 | 24 | 36 | 2012-10-04 | 2012-10-10 | 6 | 24 | 36
27 | DE.DB | Design | Database Design | Create database design decisions |  | x |  | Closed | 2012-10-11 | 2012-10-15 | 4 | 16 | 24 | 2012-10-11 | 2012-10-15 | 4 | 16 | 24 | 2012-10-11 | 2012-10-15 | 4 | 16 | 24
28 | DE.DB | Design | Interface Design | Create overview |  |  | x | Closed | 2012-10-16 | 2012-10-20 | 4 | 16 | 24 | 2012-10-16 | 2012-10-20 | 4 | 16 | 24 | 2012-10-16 | 2012-10-20 | 4 | 10 | 15
29 | DE.DB | Design | Interface Design | Create style guide |  |  | x | Updating | 2012-10-21 | 2012-10-29 | 8 | 36 | 54 | 2012-10-21 | 2012-10-29 | 7 | 30 | 45 | 2012-10-21 | 2012-11-05 | 15 | 55 | 82.5
30 | IP.CO | Implementation | Contest Management | Add contest | x |  |  | Closed | 2012-10-02 | 2012-10-02 | 0 | 4 | 8 | 2012-10-02 | 2012-10-02 | 0 | 4 | 8 | 2012-10-02 | 2012-10-02 | 0 | 4 | 8
31 | IP.CO | Implementation | Contest Management | UT feature Add contest |  | x |  | New | 2012-10-05 | 2012-10-05 | 0 | 4 | 6 | 2012-10-05 | 2012-10-05 | 0 | 4 | 6 | 2012-10-05 | 2012-10-05 | 0 | 4 | 6
32 | IP.CO | Implementation | Contest Management | edit contest | x |  |  | Closed | 2012-10-03 | 2012-10-03 | 0 | 4 | 8 | 2012-10-03 | 2012-10-03 | 0 | 4 | 8 | 2012-10-03 | 2012-10-03 | 0 | 4 | 8
33 | IP.CO | Implementation | Contest Management | UT feature edit contest |  |  | x | New | 2012-10-05 | 2012-10-05 | 0 | 4 | 6 | 2012-10-05 | 2012-10-05 | 0 | 4 | 6 | 2012-10-05 | 2012-10-05 | 0 | 4 | 6
34 | IP.CO | Implementation | Contest Management | remove contest | x |  |  | Closed | 2012-10-04 | 2012-10-04 | 0 | 4 | 8 | 2012-10-04 | 2012-10-04 | 0 | 4 | 8 | 2012-10-04 | 2012-10-04 | 0 | 4 | 8
35 | IP.CO | Implementation | Contest Management | UT feature remove contest |  | x |  | New | 2012-10-06 | 2012-10-06 | 0 | 4 | 6
36 | IP.CO | Implementation | Contest Management | contest manager page | x |  |  | New | 2012-10-05 | 2012-10-05 | 0 | 4 | 8
37 | IP.CO | Implementation | Contest Management | UT feature contest manager page |  |  | x | New | 2012-10-06 | 2012-10-06 | 0 | 4 | 6
38 | IP.CO | Implementation | Question Management | Add question | x |  |  | New | 2012-10-06 | 2012-10-06 | 0 | 4 | 8
39 | IP.CO | Implementation | Question Management | UT feature Add question |  | x |  | New | 2012-10-07 | 2012-10-07 | 0 | 4 | 6
40 | IP.CO | Implementation | Question Management | edit question | x |  |  | New | 2012-10-07 | 2012-10-07 | 0 | 4 | 8
41 | IP.CO | Implementation | Question Management | UT feature edit question |  |  | x | New | 2012-10-08 | 2012-10-08 | 0 | 4 | 6
42 | IP.CO | Implementation | Question Management | remove question | x |  |  | New | 2012-10-08 | 2012-10-08 | 0 | 4 | 8
43 | IP.CO | Implementation | Question Management | UT feature remove question |  | x |  | New | 2012-10-09 | 2012-10-09 | 0 | 4 | 6
44 | IP.CO | Implementation | Question Management | question manager page | x |  |  | New | 2012-10-09 | 2012-10-09 | 0 | 4 | 8
45 | IP.CO | Implementation | Question Management | UT feature question manager page |  |  | x | New | 2012-10-10 | 2012-10-10 | 0 | 4 | 6
46 | IP.CO | Implementation | User Management | Add user | x |  |  | New | 2012-10-10 | 2012-10-10 | 0 | 4 | 8
47 | IP.CO | Implementation | User Management | UT feature Add user |  | x |  | New | 2012-10-11 | 2012-10-11 | 0 | 4 | 6
48 | IP.CO | Implementation | User Management | edit user | x |  |  | New | 2012-10-11 | 2012-10-11 | 0 | 4 | 8
49 | IP.CO | Implementation | User Management | UT feature edit user |  |  | x | New | 2012-10-12 | 2012-10-12 | 0 | 4 | 6
50 | IP.CO | Implementation | User Management | remove user | x |  |  | New | 2012-10-12 | 2012-10-12 | 0 | 4 | 8
51 | IP.CO | Implementation | User Management | UT feature remove user |  | x |  | New | 2012-10-13 | 2012-10-13 | 0 | 4 | 6
52 | IP.CO | Implementation | User Management | user manager page | x |  |  | New | 2012-10-13 | 2012-10-13 | 0 | 4 | 8
53 | IP.CO | Implementation | User Management | UT feature user manager page |  |  | x | New | 2012-10-14 | 2012-10-14 | 0 | 4 | 6
54 | IP.CO | Implementation | Login | Login page | x |  |  | New | 2012-10-14 | 2012-10-14 | 0 | 4 | 8
55 | IP.CO | Implementation | Login | UT feature Login page |  | x |  | New | 2012-10-14 | 2012-10-14 | 0 | 4 | 6
56 | IP.CO | Implementation | Logout | Logout page | x |  |  | New | 2012-10-14 | 2012-10-14 | 0 | 4 | 8
57 | IP.CO | Implementation | Logout | UT feature Logout page |  |  | x | New | 2012-10-15 | 2012-10-15 | 0 | 4 | 6
58 | IP.CO | Implementation | Index | Index page | x |  |  | New | 2012-10-15 | 2012-10-15 | 0 | 4 | 8
59 | IP.CO | Implementation | Index | UT feature Index page |  | x |  | New | 2012-10-15 | 2012-10-15 | 0 | 4 | 6
60 | IP.CO | Implementation | Navigation Menu | Navigation Menu | x |  |  | New | 2012-10-15 | 2012-10-15 | 0 | 4 | 8
61 | IP.CO | Implementation | Navigation Menu | UT feature Navigation Menu |  |  | x | New | 2012-10-16 | 2012-10-16 | 0 | 4 | 6
62 | IP.CO | Implementation | Contest system | Contest system | x |  |  | New | 2012-10-16 | 2012-10-16 | 0 | 4 | 8
63 | IP.CO | Implementation | Contest system | UT feature Contest system |  | x |  | New | 2012-10-16 | 2012-10-16 | 0 | 4 | 6
64 | IP.CO | Implementation | Submit file system | Submit file system | x |  |  | New | 2012-10-16 | 2012-10-16 | 0 | 4 | 8
65 | IP.CO | Implementation | Submit file system | UT feature Submit file system |  |  | x | New | 2012-10-17 | 2012-10-17 | 0 | 4 | 6
66 | IP.CO | Implementation | Score table | Score table | x |  |  | New | 2012-10-17 | 2012-10-17 | 0 | 4 | 8
67 | IP.CO | Implementation | Score table | UT feature Score table |  | x |  | New | 2012-10-18 | 2012-10-18 | 0 | 4 | 6
68 | IP.CO | Implementation | About | About pages | x |  |  | New | 2012-10-18 | 2012-10-18 | 0 | 4 | 8
69 | IP.CO | Implementation | About | UT feature About pages |  |  | x | New | 2012-10-19 | 2012-10-19 | 0 | 4 | 6
70 | TE.CO
71
72
73
74
75
76
77
78
79
80
81
82

## References
Cost each hour
Leader | 2
Member | 1.5