## Phase
Project | Duy Tan Online Judge | [10 empty] | Create Date | [5 empty] | Creator
ID | [11 empty] | Updated Date | [5 empty] | Update
[12 empty] | Approved Date | [5 empty] | Approver
No | ID | Phase | Task | Task Detail | Resource |  |  |  | Plan |  |  |  |  | Performance |  |  |  |  | Actual
[5 empty] | AnhMV | AnhPV | TongTB | Status | Start | Finish | Duration (Days) | Hour | Cost | Start | Finish | Duration (Days) | Hour | Cost | Start | Finish | Duration (Days) | Hour | Cost
1 | LA.PP | Lauching | Create Proposal | Create Introduction | x |  |  | Closed | 2012-09-04 | 2012-09-04 | 0 | 2 | 4 | 2012-09-04 | 2012-09-04 | 0 | 2 | 4 | 2012-09-04 | 2012-09-04 | 0 | 1.5 | 3
2 | LA.PP | Lauching | Create Proposal | Create Vision |  | x |  | Closed | 2012-09-04 | 2012-09-04 | 0 | 2 | 3 | 2012-09-04 | 2012-09-04 | 0 | 2 | 3 | 2012-09-04 | 2012-09-04 | 0 | 1.5 | 2.25
3 | LA.PP | Lauching | Create Proposal | Create Object |  |  | x | Closed | 2012-09-04 | 2012-09-04 | 0 | 2 | 3 | 2012-09-04 | 2012-09-04 | 0 | 2 | 3 | 2012-09-04 | 2012-09-04 | 0 | 2 | 3
4 | LA.PP | Lauching | Create Proposal | Create Goals | x |  |  | Closed | 2012-09-05 | 2012-09-05 | 0 | 2 | 4 | 2012-09-05 | 2012-09-05 | 0 | 2 | 4 | 2012-09-05 | 2012-09-05 | 0 | 1.5 | 3
5 | LA.PP | Lauching | Create Proposal | Create Approach |  | x |  | Closed | 2012-09-05 | 2012-09-05 | 0 | 2 | 3 | 2012-09-05 | 2012-09-05 | 0 | 2 | 3 | 2012-09-05 | 2012-09-05 | 0 | 2 | 3
6 | LA.PP | Lauching | Create Proposal | Create Milestone |  |  | x | Closed | 2012-09-05 | 2012-09-05 | 0 | 2 | 3 | 2012-09-05 | 2012-09-05 | 0 | 2 | 3 | 2012-09-05 | 2012-09-05 | 0 | 2 | 3
7 | LA.PP | Lauching | Create Proposal | Create Resource |  | x |  | Closed | 2012-09-06 | 2012-09-06 | 0 | 2 | 3 | 2012-09-06 | 2012-09-06 | 0 | 2 | 3 | 2012-09-06 | 2012-09-06 | 0 | 1.5 | 2.25
8 | LA.PP | Lauching | Create Proposal | Create Approval | x |  |  | Closed | 2012-09-06 | 2012-09-06 | 0 | 2 | 4 | 2012-09-06 | 2012-09-06 | 0 | 2 | 4 | 2012-09-06 | 2012-09-06 | 0 | 2.5 | 5
9 | LA.TN | Lauching | Trainning | Learn and understand requirement | x | x | x | Closed | 2012-09-07 | 2012-09-07 | 0 | 9 | 45 | 2012-09-07 | 2012-09-07 | 0 | 9 | 45 | 2012-09-07 | 2012-09-07 | 0 | 7 | 35
10 | LA.TN | Lauching | Trainning | Analysis SRS sample | x | x | x | Closed | 2012-09-08 | 2012-09-08 | 0 | 9 | 45 | 2012-09-08 | 2012-09-08 | 0 | 8 | 40 | 2012-09-08 | 2012-09-08 | 0 | 7 | 35
11 | LA.TN | Lauching | Trainning | DB Design document | x | x | x | Closed | 2012-09-09 | 2012-09-09 | 0 | 9 | 45 | 2012-09-09 | 2012-09-09 | 0 | 12 | 60 | 2012-09-09 | 2012-09-09 | 0 | 7 | 35
12 | LA.TN | Lauching | Trainning | Interface design document | x | x | x | Closed | 2012-09-10 | 2012-09-11 | 1 | 18 | 90 | 2012-09-10 | 2012-09-11 | 1 | 15 | 75 | 2012-09-10 | 2012-09-11 | 1 | 14.5 | 72.5
13 | LA.TN | Lauching | Trainning | MVC | x | x | x | Closed | 2012-09-12 | 2012-09-12 | 0 | 12 | 60 | 2012-09-12 | 2012-09-12 | 0 | 15 | 75 | 2012-09-12 | 2012-09-12 | 0 | 12 | 60
14 | RE.ANA | Requirement | Analysis Requirement | Collection requirements | x | x | x | Closed | 2012-09-13 | 2012-09-13 | 0 | 12 | 60 | 2012-09-13 | 2012-09-13 | 0 | 13 | 65 | 2012-09-13 | 2012-09-13 | 0 | 12.5 | 62.5
15 | RE.ANA | Requirement | Analysis Requirement | Analysis requirements | x | x | x | Closed | 2012-09-17 | 2012-09-18 | 1 | 24 | 120 | 2012-09-17 | 2012-09-18 | 1 | 20 | 100 | 2012-09-17 | 2012-09-18 | 1 | 19.5 | 97.5
16 | RE.ANA | Requirement | Analysis Requirement | Remove requirement | x | x | x | Closed | 2012-09-14 | 2012-09-14 | 0 | 12 | 60 | 2012-09-14 | 2012-09-14 | 0 | 14 | 70 | 2012-09-14 | 2012-09-14 | 0 | 12 | 60
17 | RE.SRS | Requirement | Create SRS | Create Introduction | x |  |  | Closed | 2012-09-19 | 2012-09-20 | 1 | 8 | 16 | 2012-09-19 | 2012-09-20 | 1 | 8 | 16 | 2012-09-19 | 2012-09-20 | 1 | 9 | 18
18 | RE.SRS | Requirement | Create SRS | Create Overall Description |  | x |  | Closed | 2012-09-21 | 2012-09-23 | 2 | 12 | 18 | 2012-09-21 | 2012-09-23 | 2 | 12 | 18 | 2012-09-21 | 2012-09-23 | 2 | 7.5 | 11.25
19 | RE.SRS | Requirement | Create SRS | Create Users classes and Characterisstics |  | x |  | Closed | 2012-09-24 | 2012-09-25 | 1 | 8 | 12 | 2012-09-24 | 2012-09-25 | 1 | 8 | 12 | 2012-09-24 | 2012-09-25 | 1 | 5 | 7.5
20 | RE.SRS | Requirement | Create SRS | Create System Features | x | x | x | Closed | 2012-09-26 | 2012-09-28 | 2 | 36 | 180 | 2012-09-26 | 2012-09-28 | 2 | 33 | 165 | 2012-09-26 | 2012-09-30 | 4 | 36 | 180
21 | RE.SRS | Requirement | Create SRS | Create External Interface Requirements | x | x | x | Pending | 2012-09-29 | 2012-10-01 | 2 | 36 | 180 | 2012-09-29 | 2012-10-01 | 2 | 35 | 175 | 2012-09-29 | 2012-10-01 | 2 | 22.5 | 112.5
22 | RE.SRS | Requirement | Create SRS | Create Other Nonfunctional Requirements |  | x | x | Closed | 2012-09-29 | 2012-10-01 | 2 | 24 | 72 | 2012-09-29 | 2012-09-30 | 1 | 22 | 66 | 2012-09-29 | 2012-10-01 | 2 | 18 | 54
23 | DE.DB | Design | Database Design | Create Introduction |  | x |  | Closed | 2012-10-02 | 2012-10-02 | 0 | 4 | 6 | 2012-10-02 | 2012-10-02 | 0 | 4 | 6 | 2012-10-02 | 2012-10-02 | 0 | 2 | 3
24 | DE.DB | Design | Database Design | Create scope |  | x |  | Closed | 2012-10-03 | 2012-10-03 | 0 | 4 | 6 | 2012-10-03 | 2012-10-03 | 0 | 4 | 6 | 2012-10-03 | 2012-10-03 | 0 | 1 | 1.5
25 | DE.DB | Design | Database Design | Create sub application/Application Overview |  | x |  | Closed | 2012-10-04 | 2012-10-05 | 1 | 8 | 12 | 2012-10-04 | 2012-10-05 | 1 | 8 | 12 | 2012-10-04 | 2012-10-05 | 1 | 3.5 | 5.25
26 | DE.DB | Design | Database Design | Create table relationship diagrams |  | x |  | Closed | 2012-10-04 | 2012-10-10 | 6 | 24 | 36 | 2012-10-04 | 2012-10-10 | 6 | 24 | 36 | 2012-10-04 | 2012-10-10 | 6 | 15 | 22.5
27 | DE.DB | Design | Database Design | Create database design decisions |  | x |  | Closed | 2012-10-11 | 2012-10-15 | 4 | 16 | 24 | 2012-10-11 | 2012-10-15 | 4 | 16 | 24 | 2012-10-11 | 2012-10-15 | 4 | 9.5 | 14.25
28 | DE.DB | Design | Interface Design | Create overview |  |  | x | Closed | 2012-10-16 | 2012-10-20 | 4 | 16 | 24 | 2012-10-16 | 2012-10-20 | 4 | 16 | 24 | 2012-10-16 | 2012-10-20 | 4 | 10 | 15
29 | DE.DB | Design | Interface Design | Create style guide |  |  | x | Updating | 2012-10-21 | 2012-10-29 | 8 | 36 | 54 | 2012-10-21 | 2012-10-29 | 7 | 30 | 45 | 2012-10-21 | 2012-11-05 | 15 | 55 | 82.5
30 | IP.CO | Implementation | Contest Management | Add contest | x |  |  | Closed | 2012-11-02 | 2012-11-02 | 0 | 4 | 8 | 2012-11-02 | 2012-11-02 | 0 | 4 | 8 | 2012-11-02 | 2012-11-02 | 0 | 3 | 6
31 | IP.CO | Implementation | Contest Management | UT feature Add contest |  | x |  | New | 2012-11-05 | 2012-11-05 | 0 | 4 | 6 | 2012-11-03 | 2012-11-03 | 0 | 4 | 6 | 2012-11-03 | 2012-11-03 | 0 | 4 | 6
32 | IP.CO | Implementation | Contest Management | edit contest | x |  |  | Closed | 2012-11-03 | 2012-11-03 | 0 | 4 | 8 | 2012-11-04 | 2012-11-04 | 0 | 4 | 8 | 2012-11-03 | 2012-11-03 | 0 | 2 | 4
33 | IP.CO | Implementation | Contest Management | UT feature edit contest |  |  | x | New | 2012-11-05 | 2012-11-05 | 0 | 4 | 6 | 2012-10-05 | 2012-10-05 | 0 | 4 | 6 | 2012-10-05 | 2012-10-05 | 0 | 4 | 6
34 | IP.CO | Implementation | Contest Management | remove contest | x |  |  | Closed | 2012-11-04 | 2012-11-04 | 0 | 4 | 8 | 2012-11-04 | 2012-11-04 | 0 | 4 | 8 | 2012-11-04 | 2012-11-04 | 0 | 3 | 6
35 | IP.CO | Implementation | Contest Management | UT feature remove contest |  | x |  | New | 2012-11-06 | 2012-11-06 | 0 | 4 | 6 | 2012-11-06 | 2012-11-06 | 0 | 4 | 0
36 | IP.CO | Implementation | Contest Management | contest manager page | x |  |  | New | 2012-11-05 | 2012-11-05 | 0 | 4 | 8 | 2012-11-05 | 2012-11-05 | 0 | 4 | 8 | 2012-11-05 | 2012-11-05 | 0 | 1 | 2
37 | IP.CO | Implementation | Contest Management | UT feature contest manager page |  |  | x | New | 2012-11-06 | 2012-11-06 | 0 | 4 | 6
38 | IP.CO | Implementation | Question Management | Add question | x |  |  | New | 2012-11-06 | 2012-11-06 | 0 | 4 | 8
39 | IP.CO | Implementation | Question Management | UT feature Add question |  | x |  | New | 2012-11-07 | 2012-11-07 | 0 | 4 | 6
40 | IP.CO | Implementation | Question Management | edit question | x |  |  | New | 2012-11-07 | 2012-11-07 | 0 | 4 | 8
41 | IP.CO | Implementation | Question Management | UT feature edit question |  |  | x | New | 2012-11-08 | 2012-11-08 | 0 | 4 | 6
42 | IP.CO | Implementation | Question Management | remove question | x |  |  | New | 2012-11-08 | 2012-11-08 | 0 | 4 | 8
43 | IP.CO | Implementation | Question Management | UT feature remove question |  | x |  | New | 2012-11-09 | 2012-11-09 | 0 | 4 | 6
44 | IP.CO | Implementation | Question Management | question manager page | x |  |  | New | 2012-11-09 | 2012-11-09 | 0 | 4 | 8
45 | IP.CO | Implementation | Question Management | UT feature question manager page |  |  | x | New | 2012-11-10 | 2012-11-10 | 0 | 4 | 6
46 | IP.CO | Implementation | User Management | Add user | x |  |  | New | 2012-11-10 | 2012-11-10 | 0 | 4 | 8
47 | IP.CO | Implementation | User Management | UT feature Add user |  | x |  | New | 2012-11-11 | 2012-11-11 | 0 | 4 | 6
48 | IP.CO | Implementation | User Management | edit user | x |  |  | New | 2112-11-11 | 2112-11-11 | 0 | 4 | 8
49 | IP.CO | Implementation | User Management | UT feature edit user |  |  | x | New | 2012-11-12 | 2012-11-12 | 0 | 4 | 6
50 | IP.CO | Implementation | User Management | remove user | x |  |  | New | 2012-11-12 | 2012-11-12 | 0 | 4 | 8
51 | IP.CO | Implementation | User Management | UT feature remove user |  | x |  | New | 2012-11-13 | 2012-11-13 | 0 | 4 | 6
52 | IP.CO | Implementation | User Management | user manager page | x |  |  | New | 2012-11-13 | 2012-11-13 | 0 | 4 | 8
53 | IP.CO | Implementation | User Management | UT feature user manager page |  |  | x | New | 2012-11-14 | 2012-11-14 | 0 | 4 | 6
54 | IP.CO | Implementation | Login | Login page | x |  |  | New | 2012-11-14 | 2012-11-14 | 0 | 4 | 8
55 | IP.CO | Implementation | Login | UT feature Login page |  | x |  | New | 2012-11-14 | 2012-11-14 | 0 | 4 | 6
56 | IP.CO | Implementation | Logout | Logout page | x |  |  | New | 2012-11-14 | 2012-11-14 | 0 | 4 | 8
57 | IP.CO | Implementation | Logout | UT feature Logout page |  |  | x | New | 2012-11-15 | 2012-11-15 | 0 | 4 | 6
58 | IP.CO | Implementation | Index | Index page | x |  |  | New | 2012-11-15 | 2012-11-15 | 0 | 4 | 8
59 | IP.CO | Implementation | Index | UT feature Index page |  | x |  | New | 2012-11-15 | 2012-11-15 | 0 | 4 | 6
60 | IP.CO | Implementation | Navigation Menu | Navigation Menu | x |  |  | New | 2012-11-15 | 2012-11-15 | 0 | 4 | 8
61 | IP.CO | Implementation | Navigation Menu | UT feature Navigation Menu |  |  | x | New | 2012-11-16 | 2012-11-16 | 0 | 4 | 6
62 | IP.CO | Implementation | Contest system | Contest system | x |  |  | New | 2012-11-16 | 2012-11-16 | 0 | 4 | 8
63 | IP.CO | Implementation | Contest system | UT feature Contest system |  | x |  | New | 2012-11-16 | 2012-11-16 | 0 | 4 | 6
64 | IP.CO | Implementation | Submit file system | Submit file system | x |  |  | New | 2012-11-16 | 2012-11-16 | 0 | 4 | 8
65 | IP.CO | Implementation | Submit file system | UT feature Submit file system |  |  | x | New | 2012-11-17 | 2012-11-17 | 0 | 4 | 6
66 | IP.CO | Implementation | Score table | Score table | x |  |  | New | 2012-11-17 | 2012-11-17 | 0 | 4 | 8
67 | IP.CO | Implementation | Score table | UT feature Score table |  | x |  | New | 2012-11-18 | 2012-11-18 | 0 | 4 | 6
68 | IP.CO | Implementation | About | About pages | x |  |  | New | 2012-11-18 | 2012-11-18 | 0 | 4 | 8
69 | IP.CO | Implementation | About | UT feature About pages |  |  | x | New | 2012-11-19 | 2012-11-19 | 0 | 4 | 6
70 | TE.CO | Testing | Build Application | Build enviroment | x | x | x | New | 2012-11-22 | 2012-11-22 | 0 | 12 | 60
71 | TE.CO | Testing | Create test scenario | Create test scenario | x | x | x | New | 2012-11-26 | 2012-11-28 | 2 | 16 | 80
72 | TE.CO | Testing | Create test case | Create test case | x | x | x | New | 2012-11-29 | 2012-12-01 | 2 | 16 | 80
73 | TE.CO | Testing | Evidence | Capture evidence | x | x | x | New | 2012-12-02 | 2012-12-06 | 4 | 16 | 80
74 | TE.CO | Testing | Report | Create Report | x | x | x | New | 2012-12-07 | 2012-12-07 | 0 | 16 | 80
75 | DE.DE | Deliver | Deliver | Deliver | x | x | x | New | 2012-12-11 | 2012-12-11 | 0 | 4 | 20
76
77
78
79
80
81
82
1872

## References
Cost each hour
Leader | 2
Member | 1.5