## Guideline
GUIDELINE OF REQUIREMENT MANAGEMENT
1. Purpose
Requirement Management sheet (RM sheet) is a tool for managing project requirements by:
|  | 1.1 | Recording and tracking ALL of requirements and their changes of the projects in order not to miss or misunderstand customer requirements.
|  | 1.2 | Aligning the changing customer requirements with the products your project developed. Besides, it helps in determining the impact of a change to the system requirements, ensuring all the requirements are covered/ implemented fully throughout all activities/phases of the projects. This is also help in investigating and impact analysing changes to the requirements.
The document contains
RequirementManagement sheet: to record and track all requirements over project implementation life (including Changed requirements and Cancelled requirements).
TraceAbilityMatrix sheet: is to describe and follow the life of a requirement, in both a forward and backward direction, throughout the project life cycle. correlates any two baselined documents that require a many-to-many relationship to determine the completeness of the relationship. It is often used with customer requirements to the matching parts of Requirement specification, Design, Source code, Test cases and release of the software product. On the other hand the relationship among requirements are also be traced.
RequirementStatus_Flow sheet: provide guidance of Requirement status flow.
InfoData sheet: contains based data for combo boxes used in the documents is hidden. To unhide sheet to view the information, implement the following steps:
Step 1: Menu -> Format -> Sheet -> Unhide.
Step 2 : On Unhide, select InfoData, click OK.
After unhide sheet InfoData, you could change correspondent list item with your project information.
After changed, you to hide the sheet by
Step 1: Active the sheet to be hide.
Step 2: Menu -> Format -> Sheet -> Hide
2. Definition & Criteria
REQ ID is the unique identifying number of the requirement.
Title of REQ: one-line description of the REQ
Description of Requirement give brief information of the requirement or specify URD and SRS section(s) or link to the record where the description of requirements is recorded.
Type: New or Change Request, where Change Request are the changes to existing requirements. For fix price projects, any one or a group of new requirements come after the 1st baselined version of requirement document will be considered as Change Request also.
Size: be reflected by amount of work/effort needed to implement this REQ. It is used to measure the Requirement Completeness.
Key: the requirements are very important, have significant impact on product/process quality, functionality. It means that if the key requirements are not implemented, product/process quality, functionality does not function at all or crashes.
Priority: urgency of implementation. This field is optional.
Person in charge: Person who is assigned responsibility for implementing the change. This field is optional.
Effort: estimated effort needed to implement the requirement. This field is recommended to Change Request, and optional, could be omitted to New REQ.
Status: current status of the change request as it moves through the states described in the RequirementFlow sheet.
3. Procedure of Requirement Management
a- Requirement Management
|  | a-1 | Every requirement is registered in a separate row.
|  | a-2 | It is recommended to modify/add information as they changed as following:
a) As new requirement come, add one more row to record that requirement, record its "Type" as New.
b) As customer change the existing requirements, update description of the corresponding requirement and change its "Type" as Change Request. For fix price projects, any one or a group of new requirements come after the 1st baselined version of requirement document will be considered as Change Request also.
c) As customer requires to remove a requirement, its "Status" is changed to Cancelled.
d) As any of new requirements come, and it is a child requirement of any other requirement, add one more row below its Parent REQ to record the requirement and get REQ ID to reflect the relationship.
|  | a-3 | REQ ID shall to set by the project according to the pre-defined rule so that it is to easy to understand, easy to search. The requirements have relationship with each other should have a common identity in their ID. Parent-child relationship among require requirements must be realized via REQ ID.
|  | a-4 | Person in charge, status and expected completion date of every requirement to be identified. It could be tracked in other documents of the project (for instance: project schedule, project tasklist).
Attention: In order to ensure integrity of the information among the sheets, it is recommended to click "Add row" or "Delete row" to insert, delete row in the sheets.
b- Traceability Matrix
|  | b-1 | Requirement information in that sheet is integrated from the sheet “RequirementManagement".
|  | b-2 | Every part of other products of project (System Requirement, Design, code, test…) is recorded in a separate column with the name of the parent products.
|  | b-3 | As new requirements come or new products developed, new columns are inserted in that sheet.
|  | b-4 | To trace relation of products to requirements, we mark in correspondent cells of the requirements (driver) and the products (satisfier). The relationship of driver to satisfier can be one-to-one, one-to-many, many-to-one, or many-to-many. Traceability requires unique identifiers (ID) for each requirement and product.
・basically 1 day 1 time
・basically 1 day 1 time
・basically 1 day 1 time
・basically 1 day 1 time

## Requirement Management
Requirement Manager Sheet
Req ID | Req Title | Desciprtion | Type | Size | Key | Priority | PIC | Status | Change Status Date | Submitted Date | Committed Date | Designed Date | Design Review Date | Coded Date | Code Reviewed Date | Tested Date | Canceled Date | Note

## Trace Ability Matrix
Trace Ability Matrix
Req ID | Req Title | Description | PIC | Status | Requirement | Design | Source Code | Test Case | Other Document